## Sheet1
| User Story | Priority | Difficulty Rating | Estimated TIme (Hours) | Estimated Time (to deliverable product) | Key
| As a player, I want the game to be visually appealing | 6 | 6 | 4 | 4 | Not going to Implement
| As a player, I want the game to be technically reminiscent of the original Battleship | 1 | 4 | 6 | 6 | Total
| As a player, I want to be able to differentiate between my ships and my opponent's ships | N/A | 3 | 1 | N/A
| As a player, I want to be able to play locally against another person | 2 | 6 | 6 | 6
| As a player, I want to be able to interact with the different pieces via a GUI | 3 | 5 | 4 | 4
| If someone has never played Battleship, I want to be able to look at the rules in-game | 4 | 3 | 1 | 1
| An an experienced Battleship player, I want to have alternate game modes available | 5 | 4 | 4 | 4
| As a player, I want to be able to play online with other people | 9 | 9 | 8 | N/A
| As a player, I want to hear things like missile hits and misses and other auditorial effects | 7 | 3 | 1 | 1
| As a player, I want there to be music that plays while the game is going | 8 | 2 | 1 | 1
TOTAL |  | N/A | 45 | 36 | 27
User: Casual Gamer Grandpa I have a grandson who likes to play video games, and I'd really like to connect with him through one of them. I don't know much about Fortnite, but I do remember playing Battleship with his Father when he was just a boy. I want a Battleship game that is just fun enough to warrent a few rounds of games between me and my grandson, and maybe a couple extra game modes for variety, I'll leave that to what ya'll can come up with! I don't care what it's made with, it just has to be runnable on my new computer.